## Project Planner
Hifi Corner | [5 empty] | 1 point = 1 time
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Lav hifi logo | 1 | 1 | 0 | 0 | 0%
Header (HTML/CSS) | 2 | 1 | 0 | 0 | 0%
Navigation (HTML/CSS) | 3 | 1 | 0 | 0 | 0%
Frontpage Header/nav background w/ logo (HTML/CSS) | 4 | 1 | 0 | 0 | 0%
Frontpage showroom banner (HTML/CSS) | 5 | 1 | 0 | 0 | 0%
Frontpage product hero slider (HTML/CSS) | 6 | 1 | 0 | 0 | 0%
Frontpage product hero slider funktionalitet (JS) | 7 | 2 | 0 | 0 | 0%
Frontpage social box (HTML/CSS) | 9 | 1 | 0 | 0 | 0%
Frontpage social boxes grid (HTML/CSS) | 10 | 1 | 0 | 0 | 0%
Frontpage history/news/shop single item (HTML/CSS) | 11 | 1 | 0 | 0 | 0%
Frontpage history/news/shop grid (HTML) | 12 | 1 | 0 | 0 | 0%
Footer (HTML/CSS) | 13 | 1 | 0 | 0 | 0%
Brandspage banner (HTML) | 14 | 1 | 0 | 0 | 0%
brandspage brands we stock section (HTML/CSS) | 15 | 1 | 0 | 0 | 0%
Brandspage brandsinfo section (HTML/CSS) | 16 | 1 | 0 | 0 | 0%
Shopfrontpage shop category item (HTML/CSS) | 17 | 1 | 0 | 0 | 0%
Shopfrontpage shop categories grid (HTML/CSS) | 18 | 1 | 0 | 0 | 0%
Shop category list page middle sort by (HTML/CSS) | 19 | 1 | 0 | 0 | 0%
Shop category list page nuværende nav sted (home/amplifiers) (HTML/CSS) | 20 | 1 | 0 | 0 | 0%
Shop category list page category filter left (HTML/CSS) | 21 | 1 | 0 | 0 | 0%
Shop category list page shop by filters (HTML/CSS) | 22 | 1 | 0 | 0 | 0%
Shop category list page shop item (HTML/CSS) | 23 | 1 | 0 | 0 | 0%
Shop category list page shop item grid (HTML/CSS) | 24 | 1 | 0 | 0 | 0%
Shop category list page fetch items (JS) | 25 | 1 | 0 | 0 | 0%
Single product view banner (HTML/CSS) | 26 | 1 | 0 | 0 | 0%
Single product view item gallery (HTML/CSS) | 27 | 1 | 0 | 0 | 0%
Single product view bottom left description (HTML/CSS) | 28 | 1 | 0 | 0 | 0%
Single product view quantity and finish (HTML/CSS) | 29 | 1 | 0 | 0 | 0%
Single product view additional information (HTML/CSS) | 30 | 1 | 0 | 0 | 0%
Single product view about/price/buttons (HTML) | 31 | 1 | 0 | 0 | 0%
Single product view gallery image change (Javascript) | 32 | 5 | 0 | 0 | 0%
Single product view URLSearchParam get item json (Javascript) | 37 | 5 | 0 | 0 | 0%
Shop category list page category filtrering efter bruger valg (JS) | 42 | 6 | 0 | 0 | 0%